## Sheet1
ID | Story | Estimation (hours) | Priority (1-5) | Sprint When Finished
1 | Set Sponsor Priorities | 1 | 5 | 1
2 | Develop Tournament Format | 3 | 3 | 1
3 | Create Team Google Drive | 0 | 1 | 1
4 | Adapt Connect4 Game Engine | 5 | 5 | 1
12 | File Upload Testing | 3 | 3 | 1
13 | Sprint 1 Demo | 4 | 5 | 1
7 | Deploying to Google | 10 | 2 | 2
9 | Database Backend | 4 | 4 | 2
10 | Login Systems | 8 | 2 | 2
11 | JSON Tournament Results | 2 | 1 | 2
5 | Selectible Ais | 3 | 3 | 2
6 | User Profiles | 10 | 2 | 2
8 | Develop Player Classes | 5 | 3 | 2
15 | Docker Containers for Tournaments | 4 | 5 | 3
17 | Improve User Interfaces | 2 | 1 | 3
18 | Secure Systems with Cyber advisors (SQL injection, malware, etc.) | 10 | 5 | 3
14 | Elo Ranking System | 8 | 3 | DNF
16 | Develop User Pages | 3 | 3 | DNF
4
5
6